## README
Lab 4 - Estimation Workbook (spreadsheet tool)
Zainab ¦ SP24-BSE-034 ¦ Built on the Lab 3 backlog
Blue text = cells you edit with real session data (member estimates, AI estimates, velocity inputs). Black = formulas.
Step 1: each member writes their estimate BEFORE anyone speaks (use a stopwatch/timer), then fill Blind_Estimates.
Step 2: get AI estimates and fill AI_Comparison. Step 3: Gaps. Step 4: Sprint_Capacity.
The Member A/B/C numbers and AI numbers are sample values. Replace with your group's real written estimates.

## Blind_Estimates
Task 1 - Blind estimates (Fibonacci scale), then reveal
ID | Story | Member A | Member B | Member C | Agreed | Min | Max | Spread | All identical?
US-01 | Login | 3 | 5 | 3 | 3 | 3 | 5 | 2 | no
US-02 | Browse events | 2 | 3 | 2 | 3 | 2 | 3 | 1 | no
US-03 | Register for event | 8 | 5 | 8 | 8 | 5 | 8 | 3 | no
US-04 | Cancel registration | 3 | 3 | 5 | 3 | 3 | 5 | 2 | no
US-05 | Reminder before event | 8 | 13 | 8 | 8 | 8 | 13 | 5 | no
US-06 | Admin add event | 5 | 3 | 5 | 5 | 3 | 5 | 2 | no
US-07 | Admin remove event | 2 | 3 | 3 | 3 | 2 | 3 | 1 | no
US-08 | View my registrations | 3 | 2 | 3 | 3 | 2 | 3 | 1 | no
US-11 | Admin edit event | 5 | 5 | 3 | 5 | 3 | 5 | 2 | no
US-12 | Notify on cancellation | 8 | 8 | 13 | 8 | 8 | 13 | 5 | no
| Total agreed points |  |  |  | 49
| Stories with identical estimates |  |  |  | 0
| Largest spread |  |  |  | 5
| Timestamp / witness of blind round: | (write date, time and witness name here)

## AI_Comparison
Task 2 - AI as a fourth voice, with assumption audit
ID | Story | Team | AI | Diff (team - AI) | Abs diff | AI justification | Audit verdict | Reason for verdict
US-01 | Login | 3 | 3 | 0 | 0 | Standard auth flow | Assumed | Auth method not in backlog
US-02 | Browse events | 3 | 2 | 1 | 1 | Read-only list | Knowable | Browsing is read-only in the story
US-03 | Register for event | 8 | 5 | 3 | 3 | Concurrency on last seat | Assumed | Story does not mention seat limits
US-04 | Cancel registration | 3 | 3 | 0 | 0 | Reverse of register, frees spot | Knowable | Stated in the story
US-05 | Reminder before event | 8 | 5 | 3 | 3 | Scheduled email job | Assumed | Channel and scheduler not specified
US-06 | Admin add event | 5 | 3 | 2 | 2 | Simple CRUD form | Assumed | Assumes an admin UI already exists
US-07 | Admin remove event | 3 | 2 | 1 | 1 | Delete a record | Assumed | Ignores existing registrations
US-08 | View my registrations | 3 | 2 | 1 | 1 | Query and list | Knowable | Read-only list in the story
US-11 | Admin edit event | 5 | 3 | 2 | 2 | Reuse the add form | Assumed | Form reuse is not in the backlog
US-12 | Notify on cancellation | 8 | 3 | 5 | 5 | Trigger existing notification | Assumed | Assumes reminders already built
| Totals | 49 | 31
| Audit: Knowable count | 3
| Audit: Assumed count | 7

## Gaps
Task 3 - Three biggest team-vs-AI gaps (concrete local knowledge)
Rank | Story | Gap (abs diff) | What the team knows that the model does not
1 | US-12 | 5 | The AI cannot know our reminder module is only designed, with no cancellation hook and no decision on email vs phone contact. Building that delivery path is most of this story.
2 | US-03 | 3 | The AI cannot know our event-capacity schema is not finalised, and that none of us has handled two students racing for the last seat in our chosen database.
3 | US-05 | 3 | The AI cannot know we have not picked a job scheduler or email provider, and that our university mail domain may rate-limit bulk mail.

## Sprint_Capacity
Task 4 - Sprint capacity and confidence
Inputs (blue = edit)
Team members | 3
Working days in sprint | 10
Focused hours per person per day | 3
Hours per story point | 4
Chosen velocity (points per sprint) | 20 | Assumption: new team, unfamiliar codebase, so rounded below the 22.5 computed from hours.
Available hours | 90
Capacity from hours (points) | 22.5
Velocity used (rounded down for buffer) | 20
Order | ID | Story | Points | Cumulative | Fits in Sprint 1?
1 | US-01 | Login | 3 | 3 | Sprint 1
2 | US-02 | Browse events | 3 | 6 | Sprint 1
3 | US-06 | Admin add event | 5 | 11 | Sprint 1
4 | US-03 | Register for event | 8 | 19 | Sprint 1
5 | US-04 | Cancel registration | 3 | 22 | Later
6 | US-05 | Reminder before event | 8 | 30 | Later
7 | US-07 | Admin remove event | 3 | 33 | Later
8 | US-08 | View my registrations | 3 | 36 | Later
9 | US-11 | Admin edit event | 5 | 41 | Later
10 | US-12 | Notify on cancellation | 8 | 49 | Later
Points committed to Sprint 1 | 19
Spare capacity | 1
Total backlog points | 49
Sprints needed (rounded up) | 3
Confidence
I expect to be wrong by about 30 percent (real velocity 14 to 26 points). At the end of the sprint I will measure points actually completed against the points committed, plus real hours spent on US-03.