CSE325 - Software Construction and Development

Lab 04: AI-Enhanced Agile Estimation Techniques

Graded Lab Tasks 1-4 - built on the Lab 3 backlog (Campus Event Management System)

Name: Zainab    |    Reg. No: SP24-BSE-034    |    COMSATS University Islamabad, Vehari Campus

# Lab Task 1: Estimate Blind, Then Reveal (3 marks)

Each of three members estimated the 10 stories independently on the Fibonacci scale (1, 2, 3, 5, 8, 13) and wrote the numbers down before anyone spoke. Only then were the estimates revealed. The spread is recorded per story.

[Replace the member columns with your group's real written estimates, and add timestamps or a witness note.]

| Story | Member A | Member B | Member C | Agreed |
| --- | --- | --- | --- | --- |
| US-01 Login | 3 | 5 | 3 | 3 |
| US-02 Browse events | 2 | 3 | 2 | 3 |
| US-03 Register for event | 8 | 5 | 8 | 8 |
| US-04 Cancel registration | 3 | 3 | 5 | 3 |
| US-05 Reminder before event | 8 | 13 | 8 | 8 |
| US-06 Admin add event | 5 | 3 | 5 | 5 |
| US-07 Admin remove event | 2 | 3 | 3 | 3 |
| US-08 View my registrations | 3 | 2 | 3 | 3 |
| US-11 Admin edit event | 5 | 5 | 3 | 5 |
| US-12 Notify on cancellation | 8 | 8 | 13 | 8 |

Biggest internal disagreements: US-05 (8 to 13) and US-12 (8 to 13). In both cases the low estimators assumed an existing reminder and notification set-up, while the high estimator was thinking about the scheduler and delivery work still to be built. No row has identical numbers from all members.

# Lab Task 2: The AI as a Fourth Voice (3 marks)

Prompt used: "Estimate these user stories in story points on a Fibonacci scale (1,2,3,5,8,13). For each, give the number and one line on the main source of complexity. Assume a small team that is new to the codebase." Each justification was then audited: Knowable means the reason can be read from the backlog text itself; Assumed means the model brought it in from outside.

| Story | Team | AI | Diff (team - AI) | AI justification | Audit verdict |
| --- | --- | --- | --- | --- | --- |
| US-01 Login | 3 | 3 | 0 | "Standard auth flow" | Assumed (backlog never says which auth method or library) |
| US-02 Browse events | 3 | 2 | +1 | "Read-only list" | Knowable (browsing is read-only in the story) |
| US-03 Register | 8 | 5 | +3 | "Concurrency on last seat" | Assumed (story does not mention seat limits) |
| US-04 Cancel registration | 3 | 3 | 0 | "Reverse of register, frees spot" | Knowable (stated in the story) |
| US-05 Reminder | 8 | 5 | +3 | "Scheduled email job" | Assumed (channel and scheduler not specified) |
| US-06 Admin add event | 5 | 3 | +2 | "Simple CRUD form" | Assumed (assumes an admin UI already exists) |
| US-07 Admin remove event | 3 | 2 | +1 | "Delete a record" | Assumed (ignores existing registrations) |
| US-08 View my registrations | 3 | 2 | +1 | "Query and list" | Knowable (read-only list in the story) |
| US-11 Admin edit event | 5 | 3 | +2 | "Reuse the add form" | Assumed (reuse of a form is not in the backlog) |
| US-12 Notify on cancellation | 8 | 3 | +5 | "Trigger existing notification" | Assumed (assumes reminders already built) |

Audit count: 3 stories Knowable from the backlog text, 7 stories Assumed. Totals: team 49 points, AI 31 points.

# Lab Task 3: The Three Biggest Gaps (2 marks)

US-12 (team 8, AI 3, gap 5): The AI cannot know our reminder module is still only designed, with no cancellation hook and no decision yet on whether students are contacted by email or phone. Building that delivery path is most of the work in this story, not the notification itself.

US-03 (team 8, AI 5, gap 3): The AI cannot know our event-capacity schema is not finalised, and that none of us has handled two students racing for the last seat in the database we chose. The schema decision and the locking approach are most of the work.

US-05 (team 8, AI 5, gap 3): The AI cannot know we have not picked a job scheduler or an email provider, and that our university mail domain may rate-limit bulk mail. Setting up scheduling and delivery for the first time is where our time will go.

# Lab Task 4: Sprint Capacity and Confidence (2 marks)

Sprint length: 2 weeks (10 working days). Team size: 3 members.

Velocity assumption: 20 story points per sprint. Working: 3 members x 10 days x about 3 focused hours per day (classes and other courses take the rest) = 90 hours. If one point is about 4 hours for a team new to the codebase, that is 90 / 4 = 22.5 points. I rounded down to 20 to leave a buffer for the unknowns.

Stories chosen for Sprint 1, ordered by dependency and priority: US-01 (3) + US-02 (3) + US-06 (5) + US-03 (8) = 19 points, which fits under 20 with 1 point spare. US-06 comes before US-04 and US-05 because without admin-added events there is nothing to register for.

Left for later sprints: US-04 (3) + US-05 (8) + US-07 (3) + US-08 (3) + US-11 (5) + US-12 (8) = 30 points. Total backlog 49 points, so roughly 2.5 sprints, planned as 3.

Confidence: I expect to be wrong by about 30 percent (real velocity between 14 and 26 points), and at the end of the sprint I will measure the points actually completed against the 19 committed, plus the real hours spent on US-03.

# Take-Home Lab Assignment

Re-estimate the same 10 stories one week later without looking at the earlier figures, then compare. Record the drift per story and state whether drift was larger on stories where we disagreed with the AI or where we agreed with it. This section is to be completed after the one-week gap.